## Gantt Chart
S/No. | TASK TITLE | START DATE | DUE DATE | January | [19 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May
|  |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26 | 27
Research and Discovery
1 | Group Meeting | 2023-01-12 | 2023-01-12 | bar: January 12
2 | Research related to the project | 2023-01-13 | 2023-01-15 | bar: January 13 to January 15
3 | Group Meeting with Supervisor | 2023-01-16 | 2023-01-16 | bar: January 16
4 | Research on different types of similar usages | 2023-01-17 | 2023-01-19 | bar: January 17 to January 19
5 | Functional Requirements | 2023-01-20 | 2023-01-21 | bar: January 20 to January 21
6 | Non-functional Requirements | 2023-01-22 | 2023-01-23 | bar: January 22 to January 23
7 | Other Requirements | 2023-01-24 | 2023-01-25 | bar: January 24 to January 25
8 | Market Research | 2023-01-26 | 2023-01-27 | bar: January 26 to January 27
9 | Introduction and Overview | 2023-01-28 | 2023-01-29 | bar: January 28 to January 29
10 | Workbreakdown Structure and Gantt Chart | 2023-01-30 | 2023-01-31 | bar: January 30 to January 31
11 | Project Requirement Documentation Report | 2023-02-01 | 2023-02-02 | bar: February 1 to February 2
12 | Group Meeting to review member's research | 2023-02-02 | 2023-02-02 | bar: February 2
13 | Use Case Diagrams | 2023-02-02 | 2023-02-04 | bar: February 2 to February 4
14 | Research on the different softwares | 2023-02-05 | 2023-02-07 | bar: February 5 to February 7
15 | Project Requirement Documentation Report | 2023-02-08 | 2023-02-10 | bar: February 8 to February 10
16 | Creation of GitLab and sharing access | 2023-02-08 | 2023-02-10 | bar: February 8 to February 10
Design and Development Phase:
17 | Create Database | 2023-02-08 | 2023-02-12 | bar: February 8 to February 12
18 | Creation of Login Page for Customer | 2023-02-10 | 2023-02-14 | bar: February 10 to February 14
19 | Creation of wireframes for Website | 2023-02-14 | 2023-02-22 | bar: February 14 to February 22
20 | Creation of wireframes for Mobile App | 2023-02-15 | 2023-02-22 | bar: February 15 to February 22
21 | Create homepage for website | 2023-02-22 | 2023-03-01 | bar: February 22 to March 1
22 | Trial of linking website database with mobile application | 2023-02-25 | 2023-03-01 | bar: February 25 to March 1
23 | Creation of Rooms, Reservation, About, Contact Us Pages for Website | 2023-03-01 | 2023-03-07 | bar: March 1 to March 7
24 | Login Page for Mobile App | 2023-03-02 | 2023-03-08 | bar: March 2 to March 8
25 | Creationg of more tables in the database | 2023-03-09 | 2023-03-13 | bar: March 8 to March 13
26 | Create Login page and dahboard for System Admin and Hotel Operator | 2023-03-10 | 2023-03-15 | bar: March 10 to March 15
27 | Create website interfaces for hotel operator | 2023-03-16 | 2023-03-23 | bar: March 16 to March 23
28 | Create QR Scanner for Mobile App | 2023-03-18 | 2023-03-23 | bar: March 18 to March 23
29 | Create website interfaces for system admin | 2023-03-24 | 2023-03-30 | bar: March 24 to March 30
30 | Create website interfaces for customer | 2023-03-25 | 2023-03-31 | bar: March 25 to March 31
31 | Trial of generating QR codes | 2023-04-01 | 2023-04-05 | bar: April 1 to April 5
32 | Implement main website to online server | 2023-04-06 | 2023-04-10 | bar: April 6 to April 10
33 | Adding more functions to customer | 2023-04-06 | 2023-04-12 | bar: April 6 to April 12
34 | Testing of the main website in online server | 2023-04-08 | 2023-04-13 | bar: April 8 to April 13
35 | Implement system admin website to online server | 2023-04-14 | 2023-04-19 | bar: April 14 to April 19
36 | Testing of the system admin website in online server | 2023-04-15 | 2023-04-20 | bar: April 15 to April 20
37 | Changing interface of system admin | 2023-04-21 | 2023-04-27 | bar: April 21 to April 27
38 | Creation of more functions in the main website | 2023-04-28 | 2023-05-05 | bar: April 28 to May 5
39 | Changing of payment process | 2023-05-01 | 2023-05-05 | bar: May 1 to May 5
40 | Authenication process in Mobile App | 2023-05-01 | 2023-05-07 | bar: May 1 to May 7
41 | Adding of validation | 2023-04-20 | 2023-05-10 | bar: April 20 to May 10
Dcoumenation and Testing Phase:
42 | Testing of website and server | 2023-05-08 | 2023-05-17 | bar: May 8 to May 17
43 | Error fixing of website server | 2023-05-09 | 2023-05-17 | bar: May 9 to May 17
44 | Demonstration Video | 2023-05-17 | 2023-05-19 | bar: May 17 to May 19
45 | Test Cases | 2023-04-20 | 2023-05-19 | bar: April 20 to May 19
46 | User Manual | 2023-04-20 | 2023-05-19 | bar: April 20 to May 19
47 | Project Requirements | 2023-05-01 | 2023-05-19 | bar: May 1 to May 19
48 | Presenation Slides | 2023-05-09 | 2023-05-19 | bar: May 9 to May 19
49 | Progress Report | 2023-05-13 | 2023-05-19 | bar: May 13 to May 19
50 | Preparation for Final Presentation | 2023-05-20 | 2023-05-27 | bar: May 20 to May 27